## Deadline Risk Predictor
Imminent Deadline Risk Predictor
Total Projects Tracked: | 124
High Risk Projects: | 48
Medium Risk Projects: | 49
Low Risk Projects: | 27
Task Name | Tasks Completed | Total Tasks | Days Left | % Work Remaining | Risk of Missing Deadline (%) | Risk Level
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
E-Commerce Payment Gateway | 4 | 10 | 3 | 60% | 200% | High Risk
Core Engine Migration | 7 | 12 | 4 | 41.67% | 104.2% | High Risk
API Gateway Overhaul | 5 | 9 | 6 | 44.44% | 74.07% | Medium Risk
Auth0 Integration | 9 | 10 | 2 | 10% | 50% | Low Risk
Android App v2.0 | 4 | 15 | 10 | 73.33% | 73.33% | Medium Risk
iOS Push Notifications | 6 | 8 | 1 | 25% | 250% | High Risk
Legacy DB Refactoring | 3 | 14 | 8 | 78.57% | 98.21% | Medium Risk
Stripe Checkout Flow | 8 | 11 | 5 | 27.27% | 54.55% | Medium Risk
Cloud Backup Automation | 10 | 10 | 3 | 0% | 0% | Low Risk
UI Design System Update | 5 | 13 | 7 | 61.54% | 87.91% | Medium Risk
CI/CD Pipeline Setup | 6 | 9 | 2 | 33.33% | 166.7% | High Risk
Microservices Split | 2 | 16 | 12 | 87.5% | 72.92% | Medium Risk
Admin Analytics Panel | 7 | 10 | 4 | 30% | 75% | Medium Risk
Q3 Brand Refresh | 9 | 12 | 6 | 25% | 41.67% | Low Risk
SEO Blog Campaign | 4 | 10 | 3 | 60% | 200% | High Risk
Black Friday Email Flow | 6 | 8 | 1 | 25% | 250% | High Risk
Influencer Outreach v1 | 3 | 11 | 9 | 72.73% | 80.81% | Medium Risk
PPC Landing Page Build | 8 | 9 | 2 | 11.11% | 55.56% | Medium Risk
Product Hunt Launch | 5 | 7 | 1 | 28.57% | 285.7% | High Risk
Customer Survey Design | 10 | 12 | 5 | 16.67% | 33.33% | Low Risk
Podcast Season 2 Promo | 2 | 9 | 4 | 77.78% | 194.4% | High Risk
Video Ad Production | 6 | 14 | 7 | 57.14% | 81.63% | Medium Risk
Affiliate Portal Launch | 4 | 10 | 2 | 60% | 300% | High Risk
Newsletter Re-engagement | 9 | 9 | 3 | 0% | 0% | Low Risk
Ebook Lead Magnet | 3 | 8 | 6 | 62.5% | 104.2% | High Risk
New Employee Handbooks | 7 | 10 | 5 | 30% | 60% | Medium Risk
ATS Platform Evaluation | 5 | 12 | 8 | 58.33% | 72.92% | Medium Risk
Q2 Financial Audit | 8 | 8 | 1 | 0% | 0% | Low Risk
Office Relocation Plan | 4 | 15 | 10 | 73.33% | 73.33% | Medium Risk
Payroll Vendor Switch | 6 | 9 | 3 | 33.33% | 111.1% | High Risk
Remote Work Policy Update | 9 | 11 | 4 | 18.18% | 45.45% | Low Risk
Annual Tax Filing | 7 | 7 | 2 | 0% | 0% | Low Risk
KPI Dashboard Build | 3 | 10 | 6 | 70% | 116.7% | High Risk
Inventory Audit 2026 | 8 | 13 | 5 | 38.46% | 76.92% | Medium Risk
CRM Data Cleansing | 5 | 9 | 2 | 44.44% | 222.2% | High Risk
Travel Expense Policy | 10 | 10 | 4 | 0% | 0% | Low Risk
Manager Training Program | 4 | 12 | 9 | 66.67% | 74.07% | Medium Risk
Mobile Onboarding UX | 6 | 11 | 3 | 45.45% | 151.5% | High Risk
Figma Component Audit | 9 | 9 | 1 | 0% | 0% | Low Risk
User Persona Research | 3 | 8 | 5 | 62.5% | 125% | High Risk
Dark Mode UI Theme | 7 | 14 | 6 | 50% | 83.33% | Medium Risk
Interactive Wireframes | 5 | 10 | 2 | 50% | 250% | High Risk
Competitor Analysis Repo | 8 | 12 | 7 | 33.33% | 47.62% | Low Risk
Checkout Cart Redesign | 2 | 9 | 3 | 77.78% | 259.3% | High Risk
Beta Feedback Review | 6 | 8 | 1 | 25% | 250% | High Risk
Accessibility (WCAG) Audit | 4 | 13 | 10 | 69.23% | 69.23% | Medium Risk
Landing Page Wireframes | 9 | 10 | 4 | 10% | 25% | Low Risk
Feature Prioritization Matrix | 7 | 11 | 5 | 36.36% | 72.73% | Medium Risk
Design System Audit | 5 | 9 | 2 | 44.44% | 222.2% | High Risk
SSO Authentication Rollout | 8 | 10 | 3 | 20% | 66.67% | Medium Risk
Server Patch Deployment | 6 | 7 | 1 | 14.29% | 142.9% | High Risk
Firewall Rule Audit | 3 | 12 | 8 | 75% | 93.75% | Medium Risk
MDM Device Enrollment | 9 | 9 | 2 | 0% | 0% | Low Risk
Phishing Simulation Q1 | 5 | 10 | 4 | 50% | 125% | High Risk
VPN Hardware Upgrade | 7 | 13 | 6 | 46.15% | 76.92% | Medium Risk
SOC2 Compliance Check | 4 | 8 | 1 | 50% | 500% | High Risk
AWS IAM Permission Trim | 10 | 11 | 5 | 9.091% | 18.18% | Low Risk
Data Encryption at Rest | 6 | 9 | 3 | 33.33% | 111.1% | High Risk
SaaS Tool Access Review | 8 | 12 | 7 | 33.33% | 47.62% | Low Risk
Disaster Recovery Test | 3 | 10 | 2 | 70% | 350% | High Risk
SSL Certificate Renewal | 7 | 8 | 1 | 12.5% | 125% | High Risk
Churn Prediction Model | 6 | 10 | 4 | 40% | 100% | Medium Risk
Customer Segmentation Clustering | 8 | 12 | 6 | 33.33% | 55.56% | Medium Risk
Lead Scoring Algorithm | 5 | 9 | 2 | 44.44% | 222.2% | High Risk
Sentiment Analysis Pipeline | 4 | 11 | 7 | 63.64% | 90.91% | Medium Risk
Fraud Detection Model v1 | 9 | 13 | 3 | 30.77% | 102.6% | High Risk
Sales Forecasting Dashboard | 7 | 10 | 5 | 30% | 60% | Medium Risk
NLP Chatbot Intent Engine | 3 | 9 | 8 | 66.67% | 83.33% | Medium Risk
Image Classification Baseline | 6 | 8 | 1 | 25% | 250% | High Risk
Recommendation Engine Tuning | 5 | 12 | 6 | 58.33% | 97.22% | Medium Risk
Vector Database Setup | 8 | 9 | 2 | 11.11% | 55.56% | Medium Risk
Data Pipeline Orchestration | 4 | 14 | 9 | 71.43% | 79.37% | Medium Risk
A/B Testing Framework Build | 7 | 10 | 3 | 30% | 100% | Medium Risk
Model Drift Monitoring | 9 | 11 | 4 | 18.18% | 45.45% | Low Risk
Kubernetes Cluster Autoscaling | 5 | 9 | 2 | 44.44% | 222.2% | High Risk
Terraform Modules Refactor | 6 | 13 | 7 | 53.85% | 76.92% | Medium Risk
Multi-Region Failover Test | 3 | 10 | 5 | 70% | 140% | High Risk
Docker Image Size Trimming | 8 | 8 | 1 | 0% | 0% | Low Risk
Kafka Message Broker Setup | 4 | 12 | 8 | 66.67% | 83.33% | Medium Risk
Log Aggregation (ELK Stack) | 7 | 9 | 3 | 22.22% | 74.07% | Medium Risk
CDN Edge Caching Rule Build | 9 | 10 | 2 | 10% | 50% | Low Risk
AWS Cost Optimization Audit | 5 | 11 | 6 | 54.55% | 90.91% | Medium Risk
Database Read Replica Setup | 6 | 9 | 4 | 33.33% | 83.33% | Medium Risk
Secrets Manager Integration | 8 | 7 | 1 | -14.29% | -142.9% | Low Risk
Nginx Load Balancer Tuning | 3 | 10 | 7 | 70% | 100% | Medium Risk
Serverless Function Refactor | 7 | 12 | 5 | 41.67% | 83.33% | Medium Risk
Invoice Ledger Automation | 9 | 9 | 2 | 0% | 0% | Low Risk
Multi-Currency Support Audit | 4 | 13 | 9 | 69.23% | 76.92% | Medium Risk
Payment Gateway Reconciliation | 6 | 10 | 3 | 40% | 133.3% | High Risk
Q4 Revenue Projections | 5 | 8 | 1 | 37.5% | 375% | High Risk
Tax Compliance Automation | 8 | 11 | 4 | 27.27% | 68.18% | Medium Risk
Subscription Churn Reporting | 3 | 9 | 6 | 66.67% | 111.1% | High Risk
Budget Allocation Tool v2 | 7 | 10 | 2 | 30% | 150% | High Risk
Internal Expense Auditing | 9 | 12 | 5 | 25% | 50% | Low Risk
Vendor Contract Renewals | 4 | 8 | 3 | 50% | 166.7% | High Risk
Equity Management System | 6 | 14 | 10 | 57.14% | 57.14% | Medium Risk
Risk Assessment Modeling | 5 | 9 | 2 | 44.44% | 222.2% | High Risk
Banking API Sandbox Sandbox | 8 | 10 | 4 | 20% | 50% | Low Risk
Zendesk Macro Clean-up | 3 | 7 | 1 | 57.14% | 571.4% | High Risk
IVR Phone Tree Optimization | 7 | 11 | 6 | 36.36% | 60.61% | Medium Risk
Help Center Documentation Rewrite | 5 | 9 | 3 | 44.44% | 148.1% | High Risk
SLA Breach Alerting Rule Build | 9 | 10 | 2 | 10% | 50% | Low Risk
Customer Health Score Dashboard | 4 | 12 | 8 | 66.67% | 83.33% | Medium Risk
Intercom Chatbot Playbook Build | 6 | 8 | 1 | 25% | 250% | High Risk
Support Ticket Categorization | 8 | 9 | 4 | 11.11% | 27.78% | Low Risk
NPS Survey Workflow Setup | 3 | 10 | 7 | 70% | 100% | Medium Risk
Customer Offboarding Playbook | 7 | 8 | 2 | 12.5% | 62.5% | Medium Risk
Community Forum Migration | 5 | 13 | 9 | 61.54% | 68.38% | Medium Risk
User Training Webinar Deck | 9 | 9 | 1 | 0% | 0% | Low Risk
CRM Contact Enrichment | 4 | 11 | 5 | 63.64% | 127.3% | High Risk
GDPR Data Deletion Workflow | 6 | 10 | 3 | 40% | 133.3% | High Risk
CCPA Compliance Audit | 8 | 12 | 6 | 33.33% | 55.56% | Medium Risk
Penetration Testing Remediations | 3 | 9 | 2 | 66.67% | 333.3% | High Risk
MDM Mobile Device Security | 7 | 10 | 4 | 30% | 75% | Medium Risk
Active Directory Clean-up | 5 | 8 | 1 | 37.5% | 375% | High Risk
Zero Trust Network Architecture | 9 | 14 | 8 | 35.71% | 44.64% | Low Risk
Password Manager Rollout | 4 | 9 | 3 | 55.56% | 185.2% | High Risk
Endpoint Detection Setup | 6 | 11 | 5 | 45.45% | 90.91% | Medium Risk
SaaS App Vendor Risk Check | 8 | 10 | 2 | 20% | 100% | Medium Risk
Data Loss Prevention Audit | 3 | 9 | 6 | 66.67% | 111.1% | High Risk
Incident Response Runbook Build | 7 | 12 | 4 | 41.67% | 104.2% | High Risk
Third-Party API Token Trim | 5 | 8 | 1 | 37.5% | 375% | High Risk
SOC2 Type II Readiness | 9 | 13 | 7 | 30.77% | 43.96% | Low Risk
Biometric Auth Evaluation | 6 | 9 | 2 | 33.33% | 166.7% | High Risk